## Defects
Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
|  | LangChain dependency conflict during environment setup | Sprint 1 | posham sravanthi | Logical | Updated package versions and reinstalled dependencies | 2025-12-04 | Closed | Issue resolved successfully
|  | Agent tool invocation failed for certain inputs | Sprint 2 | posham sravanthi | Logical | Modified prompt logic and added validation | 2025-12-18 | Closed | Functionality working as expected

## Sheet2
Logical
User Interface
Maintainability
Standards
Others